Tracto Designer

Sprint Plan  v1.0

8 Sprints | ~16 Weeks | DS-01..DS-19 + DESIGN-IT-01..08

| Document ID | TRACTO-DS-SPRINT-001 |
| --- | --- |
| Version | 1.0 ¦ 24 October 2026 |
| Audience | Designer team, QA lead, lead architect, project manager |
| FRD baseline | Tracto_Designer_Functional_Spec_v1_2_Features_Included.docx |
| Platform | .NET 10 / C# 14 / WPF / net10.0-windows / x64 |
| Repo | tracto-designer (C:\Users\santh\Downloads\New-NeeliRPA\tracto-designer) |
| Total sprints | 8 sprints ¦ ~16 weeks ¦ 158 story points |
| Status | DRAFT — awaiting lead architect approval |

# 1. Sprint Summary

| Sprint | Name | Duration | Stories | Exit Gate Summary | Points |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | Foundation — Session & Desktop Capture | 2 weeks | DS-01, DS-02 | DS-01 all ACs green | 21 |
| Sprint 2 | Browser + Terminal Capture & Screenshot Evidence | 2 weeks | DS-03, DS-04, DS-05, DS-06 | DS-03, DS-04, DS-05, DS-06 all ACs green | 26 |
| Sprint 3 | Normalization Pipeline & Deterministic Script Generation | 2 weeks | DS-07, DS-09 | DS-07, DS-09 all ACs green | 18 |
| Sprint 4 | Script Authoring — Editor, Selectors, Variables, Control Flow | 2 weeks | DS-10, DS-11, DS-12, DS-13 | DS-10, DS-11, DS-12, DS-13 all ACs green | 29 |
| Sprint 5 | Validation & AI Authoring Bridge | 2 weeks | DS-14, DS-08 | DS-14, DS-08 all ACs green | 22 |
| Sprint 6 | Runtime Test, Signing & Publishing | 2 weeks | DS-15, DS-16, DS-17 | DS-15, DS-16, DS-17 all ACs green | 24 |
| Sprint 7 | Offline Export, Import & Isolated Mode | 2 weeks | DS-18, DS-19 | DS-18, DS-19 all ACs green | 20 |
| Sprint 8 | Integration Scenarios, Conformance & Release | 2 weeks | DESIGN-IT-01 through DESIGN-IT-08 (all integration scenarios) | All DESIGN-IT-01..08 pass with declared fixtures | 18 |
| Total | 8 sprints · ~16 weeks |  | DS-01..DS-19 + DESIGN-IT-01..08 | All ACs green; CERTIFICATION.md written | 178 |

# 2. Sprint Detail

## Sprint 1: Foundation — Session & Desktop Capture

| Sprint Goal | A running WPF shell can start a Desktop recording session, capture UIA/JAB/keyboard events, and seal a raw event log. All optional adapter interfaces defined with null implementations so downstream sprints never need an architectural change. |
| --- | --- |
| Duration | 2 weeks |
| Stories | DS-01 ¦ DS-02 |
| Additional deliverables | • WPF shell skeleton: main window, engine selector, recording toolbar (Start / Pause / Resume / Stop / Discard) • Define IAiAuthoringAdapter, IVoiceTranscriptionAdapter, IScreenshotAdapter interfaces in Tracto.Designer.Core • NullAiAdapter, NullVoiceAdapter, NullScreenshotAdapter null implementations registered via DI • Recording session state machine: IDLE → RECORDING → PAUSED → STOPPED |
| Test coverage | Unit: session state machine, concurrent-session guard, crash detection, WinEventHook parsing, UIA ancestry chain, JAB fallback, password-field masking. Integration: start→capture→stop roundtrip against WinForms reference app fixture. |
| Exit criteria | 1. DS-01 all ACs green 2. DS-02 all ACs green 3. WPF shell launches without error; recording controls functional 4. All three adapter interfaces defined; DI wired; null adapters return safe no-op results 5. No TargetFramework specified in any .csproj (inherited from Directory.Build.props) |
| Dependencies | None — Sprint 1 is the root. |
| Risks & mitigations | WinEventHook registration may require elevated trust level on some Windows configurations. Mitigate: test against reference VM early. |
| Story points | 21 |

## Sprint 2: Browser + Terminal Capture & Screenshot Evidence

| Sprint Goal | All three capture engines are working. Screenshot evidence is captured at each significant action, with privacy masking applied before storage. Voice narration adapter wired with an approved offline STT library. |
| --- | --- |
| Duration | 2 weeks |
| Stories | DS-03 ¦ DS-04 ¦ DS-05 ¦ DS-06 |
| Additional deliverables | • Playwright for .NET browser instrumentation (CDP); headed recording mode • ConPTY terminal adapter for CMD, PowerShell; policy-allowlist enforcement • IScreenshotAdapter: real implementation capturing window state before/after each action; UIA IsPassword masking; browser input[type=password] masking • IVoiceTranscriptionAdapter: real implementation using approved offline STT library; timestamp alignment |
| Test coverage | Unit: CDP event parsing, browser selector ranking, ConPTY command-boundary detection, screenshot masking algorithm (password fields must not survive), voice alignment. Integration: full browser capture against reference web app; terminal capture against CMD/PowerShell fixtures. |
| Exit criteria | 1. DS-03, DS-04, DS-05, DS-06 all ACs green 2. Screenshot privacy: no password text survives masking in any persisted image 3. Voice narration: timestamped transcript produced from known audio file; low-confidence segments flagged 4. Policy-disallowed shell rejected at session start |
| Dependencies | DS-01 (Sprint 1) must be complete. |
| Risks & mitigations | Playwright CDP API stability; ConPTY prompt-pattern detection may miss custom prompts. Mitigate: use a canonical reference app fixture with known prompts. |
| Story points | 26 |

## Sprint 3: Normalization Pipeline & Deterministic Script Generation

| Sprint Goal | Raw events from any engine pass through the normalization pipeline into a common intermediate transcript. The deterministic generator produces a CEC-compliant DRAFT from that transcript with no AI, no network. |
| --- | --- |
| Duration | 2 weeks |
| Stories | DS-07 ¦ DS-09 |
| Additional deliverables | • Selector ranking: uiaAutomationId > className+name > ancestry > keyboard-fallback > control-relative • Sensitive-value replacement: __SECRET_PLACEHOLDER__ inserted at normalization; never survives to DRAFT • Narration segment alignment: narrationSegmentRef attached to each TranscriptEntry • Deterministic actionIntent → actionType mapping table for all three engines |
| Test coverage | Unit: each raw event type → correct TranscriptEntry; deduplication timing; selector ranking; sensitive-value replacement; unknown event flagging; each actionIntent mapping; secret placeholder → input placeholder; no-network guarantee (assert no sockets opened during generation). Integration: DS-02/03/04 raw log → normalized transcript → DS-09 DRAFT → DS-14 pre-validation clean. |
| Exit criteria | 1. DS-07, DS-09 all ACs green 2. DRAFT produced from a recorded Desktop/Browser/Terminal session without AI 3. No plaintext secret survives normalization or generation 4. Unknown events appear as review.UNKNOWN steps in DRAFT (not dropped) 5. DRAFT passes DS-14 structural schema check (pre-Sprint 5 smoke validation) |
| Dependencies | DS-01, DS-02 (Sprint 1); DS-03, DS-04, DS-05, DS-06 (Sprint 2). |
| Risks & mitigations | CEC schema may evolve as contract workstream progresses. Mitigate: pin to published Stage 1 artefact; do not invent local grammar. |
| Story points | 18 |

## Sprint 4: Script Authoring — Editor, Selectors, Variables, Control Flow

| Sprint Goal | Authors can open a DRAFT, reorder steps, edit selectors with live app feedback, declare parameters and secretRefs, and add CEC-compliant branches and loops. The editor is the primary human-in-the-loop control surface. |
| --- | --- |
| Duration | 2 weeks |
| Stories | DS-10 ¦ DS-11 ¦ DS-12 ¦ DS-13 |
| Additional deliverables | • WPF step-list editor: drag-to-reorder, step detail panel, actionType enum picker (engine-filtered) • Live selector test against running target app (read-only; UIA/Playwright probe) • SecretRef conversion wizard; parameterization suggestion for repeated literals • Control flow editor: closed-grammar predicate picker; maxIterations policy cap enforcement |
| Test coverage | Unit: reorder with backward-jump detection, deletions with reference check, runtimeType-filtered picker, live selector handlers (UIA/Playwright/PTY), ambiguous/not-found/multi-match results, secret-placeholder conversion, repeated-literal detection, closed-grammar picker filter, maxIterations enforcement, cycle detection, backward-jump detection. Integration: full editing session → DS-14 validation pass. |
| Exit criteria | 1. DS-10, DS-11, DS-12, DS-13 all ACs green 2. Live selector test returns unique / not-found / ambiguous — no crash on any outcome 3. review.UNKNOWN steps visible with 'Review required' badge; publish blocked until resolved 4. Control flow: domain expressions (amount > 10000) rejected by picker; not selectable 5. maxIterations above policy cap rejected at edit time with actual cap shown |
| Dependencies | DS-07, DS-09 (Sprint 3) — DRAFT must exist before editor is meaningful. |
| Risks & mitigations | WPF drag-and-drop reorder complexity; UIA live-probe timing on slow apps. Mitigate: test on minimum-spec VM. |
| Story points | 29 |

## Sprint 5: Validation & AI Authoring Bridge

| Sprint Goal | The CEC validator gates every publish path. The MCP AI authoring bridge lets Claude Code (or any approved client) enhance a DRAFT, with the Designer's own validator enforcing compliance. Deterministic path remains available when no AI connector is configured. |
| --- | --- |
| Duration | 2 weeks |
| Stories | DS-14 ¦ DS-08 |
| Additional deliverables | • DS-14 validator: all CEC-001..CEC-016 checks; structured violation output {severity, stepId, fieldPath, violationType, message, suggestedFix} • DS-08 MCP server on named local socket: get_transcript, get_capabilities, get_draft_script, validate_script, update_script • validate_script MCP tool and DS-14 UI validator must return identical results for all conformance test scripts • update_script: atomic apply; diff/preview shown to author before acceptance; clears prior test/signature state |
| Test coverage | Unit: each violation type with a crafted minimal script; allowlist parser boundary tests; reference resolution; each MCP tool handler; validate_script integration with DS-14; update_script atomic apply; no-network assertion (socket only). Integration: full Claude Code session — get_transcript → get_capabilities → validate loop → update_script → DRAFT updated; DS-08 and DS-14 return identical violations for same script. |
| Exit criteria | 1. DS-14, DS-08 all ACs green 2. All CEC-001..CEC-016 conformance fixtures pass validation 3. DS-08 validate_script ≡ DS-14 UI validator: identical results for all test scripts 4. Business expression (amount > 10000) rejected at both UI and MCP layer 5. No AI connector configured → deterministic DRAFT shown immediately; no MCP server started |
| Dependencies | DS-09, DS-13 (Sprint 3/4) — validator needs a DRAFT corpus to test against. |
| Risks & mitigations | MCP named socket binding may behave differently on some Windows editions. Mitigate: test on reference VM. |
| Story points | 22 |

## Sprint 6: Runtime Test, Signing & Publishing

| Sprint Goal | Authors can test a VALIDATED script by invoking the installed Desktop Runtime, then sign and publish the approved artifact to the Orchestrator registry. Version management tracks the full draft/published lifecycle. |
| --- | --- |
| Duration | 2 weeks |
| Stories | DS-15 ¦ DS-16 ¦ DS-17 |
| Additional deliverables | • DS-15: invoke versioned Desktop Runtime test harness; show step-by-step trace with SUCCEEDED/FAILED/UNKNOWN; link FAILED steps to DS-11 • DS-16: canonical JSON canonicalization + SHA-256 hash + trusted publisher key signing + POST to OC-11 • DS-16: 409 conflict handling; localhost OC-11 (isolated mode) works identically to networked mode • DS-17: version state machine (DRAFT/VALIDATED/TESTED/SIGNED/PUBLISHED/SUPERSEDED); immutability guard |
| Test coverage | Unit: step state machine for test runs, cancel path, secretRef masking in trace, hash computation, signing, 409 handling. Integration: test a known-good VALIDATED script against WinForms reference app (all steps SUCCEEDED); full publish to mock OC-11; artifact retrieved and validated by Desktop Runtime worker. |
| Exit criteria | 1. DS-15, DS-16, DS-17 all ACs green 2. DESIGN-IT-07: published script runs on Desktop Runtime end-to-end; SUCCEEDED reported 3. OC-11 409 → Designer shows 'increment version and republish'; no state corruption 4. Signing: identical scripts produce identical artifact hashes across machines 5. PUBLISHED version cannot be edited in place; new DRAFT copy created automatically |
| Dependencies | DS-14 (Sprint 5) — VALIDATED state required before signing; DS-11 (Sprint 4) — selector errors link to selector manager. |
| Risks & mitigations | OC-11 endpoint availability during integration testing. Mitigate: provide a mock OC-11 stub in the test harness from Sprint 5. |
| Story points | 24 |

## Sprint 7: Offline Export, Import & Isolated Mode

| Sprint Goal | The Designer supports fully isolated deployments: export a sanitized recording for AI-assisted authoring on a connected workstation; import a signed script package with all trust and authorization checks. The air-gapped authoring loop is complete end-to-end. |
| --- | --- |
| Duration | 2 weeks |
| Stories | DS-18 ¦ DS-19 |
| Additional deliverables | • DS-18: privacy pass (all sensitive regions re-masked or excluded); ZIP assembly; manifest SHA-256; signed package integrity • DS-18: import on connected workstation Designer → AI authoring → signed script package returned • DS-19: seven-step verification chain in order; authorization gate before registry admission; atomic rollback on OC-11 error • DS-19: independent DS-14 validation run on import (defense-in-depth) |
| Test coverage | Unit: privacy pass algorithm; package assembly; SHA-256 of ZIP; signature; each DS-19 verification check with a crafted failing package; authorization gate; atomic rollback; business expression in imported script caught independently. Integration: export on Machine A → import on Machine B → AI authoring → valid DRAFT produced (DESIGN-IT-06 roundtrip). |
| Exit criteria | 1. DS-18, DS-19 all ACs green 2. DESIGN-IT-06: full offline isolated roundtrip succeeds — record offline → export → AI author on connected machine → import → replay offline without network 3. Privacy pass: no sensitive data in any exported screenshot; excluded images logged 4. DS-19 check (7): imported script with prohibited business expression caught independently of source validator 5. Authorization gate: import blocked even after all verification checks pass, until named approver grants authorization |
| Dependencies | DS-07 (Sprint 3); DS-05, DS-06 (Sprint 2); DS-14, DS-16 (Sprints 5/6). |
| Risks & mitigations | Cross-machine integrity check requires matching signing infrastructure. Mitigate: use shared test PKI in CI. |
| Story points | 20 |

## Sprint 8: Integration Scenarios, Conformance & Release

| Sprint Goal | All 8 DESIGN-IT integration scenarios pass. Conformance is verified against published CEC Stage 1 fixtures. CERTIFICATION.md is written with evidence. The Designer is release-ready for the declared deployment profiles. |
| --- | --- |
| Duration | 2 weeks |
| Stories | DESIGN-IT-01 through DESIGN-IT-08 (all integration scenarios) |
| Additional deliverables | • DESIGN-IT-01: AI authoring scenario — record → deterministic draft → AI suggestion → review → validate → publish • DESIGN-IT-02: Browser recording → Playwright events → tested against browser fixture • DESIGN-IT-03: Terminal recording → no business-API-escape steps in published script • DESIGN-IT-04: Live selector test resolves correct element in running app • DESIGN-IT-05: Narration scenario — timestamped transcription annotates all steps • DESIGN-IT-06: Offline isolated roundtrip (Sprint 7 exit gate re-verified) • DESIGN-IT-07: Published script runs on Desktop Runtime end-to-end SUCCEEDED (Sprint 6 gate re-verified) • DESIGN-IT-08: Invalid business predicate rejected by canonical validator + MCP returns identical result • CEC Stage 1 conformance suite: all fixtures pass DS-14 + DS-08 validate_script • CERTIFICATION.md: Designer evidence table with sprint, AC, test result, tester, date, fixture |
| Test coverage | All 8 DESIGN-IT scenarios with real artifacts. Full CEC conformance fixture suite. Regression run across all DS-01..DS-19 ACs. Security review: no secret in any log, transcript, AI prompt or screenshot. |
| Exit criteria | 1. All DESIGN-IT-01..08 pass with declared fixtures 2. All DS-01..DS-19 ACs green (full regression) 3. DS-08 validate_script ≡ DS-14 UI validator for all 16 CEC conformance scripts 4. No plaintext secret in any log, transcript, AI prompt, diagnostic bundle or screenshot 5. CERTIFICATION.md written and signed off by lead architect + security reviewer 6. No open ERROR-severity violations in any VALIDATED published script |
| Dependencies | All prior sprints complete. |
| Risks & mitigations | Integration scenario failures may require targeted fixes; schedule buffer built into this sprint. Conformance fixture suite must be obtained from the Common Contract workstream before Sprint 8 starts. |
| Story points | 18 |

# 3. Sprint Dependency Map

## Sprint Dependency Map

| Sprint | Depends on | Rationale |
| --- | --- | --- |
| Sprint 1 | None | DS-01, DS-02 are the dependency roots for all subsequent work |
| Sprint 2 | Sprint 1 (DS-01) | DS-03/04/05/06 all require an active session from DS-01 |
| Sprint 3 | Sprints 1–2 | Normalization (DS-07) requires at least one capture engine |
| Sprint 4 | Sprint 3 (DS-07, DS-09) | Editor (DS-10) requires a DRAFT to open |
| Sprint 5 | Sprints 3–4 (DS-09, DS-13) | Validator needs a DRAFT corpus; AI bridge wraps DS-14 |
| Sprint 6 | Sprint 5 (DS-14) | Signing and publishing require VALIDATED state |
| Sprint 7 | Sprints 2, 3, 5, 6 | Export uses capture + normalization; import uses validator + registry |
| Sprint 8 | All prior sprints | Integration scenarios require all DS stories complete |

# 4. Adapter Delivery Schedule

## Adapter Delivery Schedule

| Adapter | Delivered in | Story | Notes |
| --- | --- | --- | --- |
| IScreenshotAdapter | Sprint 2 | DS-05 | WinGDI/WinRT screen capture; UIA IsPassword masking; browser password-field masking; policy gate per session |
| IVoiceTranscriptionAdapter | Sprint 2 | DS-06 | Approved offline STT adapter; timestamp alignment; low-confidence flagging; no network required |
| IAiAuthoringAdapter (MCP) | Sprint 5 | DS-08 | Named local socket; 5 tools: get_transcript, get_capabilities, get_draft_script, validate_script, update_script |
| Null implementations | Sprint 1 | Interfaces defined | NullScreenshotAdapter, NullVoiceAdapter, NullAiAdapter — all wired via DI from Sprint 1; replaced in later sprints |

# 5. Designer Definition of Done

## Designer Definition of Done

Each story is DONE when:

- All acceptance criteria in the FRD v1.2 pass on the reference fixture environment

- Unit tests cover every AC; integration test covers the story's end-to-end flow

- No plaintext secret survives in any log, trace, screenshot or transcript

- No TargetFramework or Nullable duplicated in any .csproj (Directory.Build.props owns it)

- PR reviewed and merged to main; CI green

The Designer is RELEASE-READY when:

- All DS-01..DS-19 ACs green on the declared certified environment

- All DESIGN-IT-01..08 integration scenarios pass with real artifacts

- DS-08 validate_script ≡ DS-14 UI validator for all CEC Stage 1 conformance scripts

- DS-18/DS-19 offline roundtrip complete (for isolated deployment profile)

- CERTIFICATION.md written: evidence table with sprint, AC, result, tester, date, fixture digest

- Security review sign-off: no secret in any diagnostic bundle, AI prompt, screenshot or telemetry

- Architecture sign-off by lead architect

# 6. Story-to-Sprint Traceability

| Story ID | Story Name | Sprint | Key dependencies | Group |
| --- | --- | --- | --- | --- |
| DS-01 | Recording Session Lifecycle | Sprint 1 | None | Foundation |
| DS-02 | Desktop Event Capture — UIA, JAB, Keyboard | Sprint 1 | DS-01 | Capture |
| DS-03 | Browser Event Capture — Playwright CDP | Sprint 2 | DS-01 | Capture |
| DS-04 | Terminal Session Capture — PTY/ConPTY | Sprint 2 | DS-01 | Capture |
| DS-05 | Screenshot Capture & Privacy Masking | Sprint 2 | DS-01 | Evidence |
| DS-06 | Voice Narration & Local Transcription | Sprint 2 | DS-01 | Evidence |
| DS-07 | Transcript Normalization | Sprint 3 | DS-02/03/04 | Pipeline |
| DS-08 | AI-Assisted Script Enhancement (MCP) | Sprint 5 | DS-07, DS-09, DS-14 | AI |
| DS-09 | Deterministic Script Generation | Sprint 3 | DS-07 | Generation |
| DS-10 | Script Editor | Sprint 4 | DS-09 | Authoring |
| DS-11 | Selector Management & Live Test | Sprint 4 | DS-02/03, DS-10 | Authoring |
| DS-12 | Variable & Parameter Extraction | Sprint 4 | DS-10 | Authoring |
| DS-13 | Control Flow Editor | Sprint 4 | DS-10, DS-14 | Authoring |
| DS-14 | Script Validation — CEC Grammar | Sprint 5 | DS-09 | Validation |
| DS-15 | Runtime-Based Script Test Execution | Sprint 6 | DS-14, DS-11 | Testing |
| DS-16 | Artifact Signing & Registry Publishing | Sprint 6 | DS-14 | Publishing |
| DS-17 | Script Version Management | Sprint 6 | DS-16 | Publishing |
| DS-18 | Offline Sanitized Recording Export | Sprint 7 | DS-07, DS-05/06 | Isolated |
| DS-19 | Signed Script Package Import & Registration | Sprint 7 | DS-14, DS-16 | Isolated |