Tracto Orchestrator

Sprint Plan  v1.0

8 Sprints  |  178 Story Points  |  OC-01–OC-17 + ORCH-IT-01–12

Based on: Tracto_Orchestrator_User_Stories_v1_1.docx

Date: 23 October 2026

# 1.  Ordering Principles

Stories are sequenced so that each sprint delivers a runnable, independently testable slice of the Orchestrator, while every sprint's output is directly depended on by the next.

- Foundation first: persistence and deployment before any domain logic.

- Build registries before consumers: artifact registry before job intake; worker registry before queue dispatch.

- Lifecycle before edge-cases: admit → lease → heartbeat → result before cancellation or reconciliation.

- Resilience after happy path: reconciliation (OC-10) requires RUNNING and terminal states (OC-06).

- Callbacks after HANDED_OFF: OC-07/08 require the terminal state that triggers them (OC-06).

- Security hardening after all API surfaces exist: OC-17 verifies controls that span every prior sprint.

- Operator tooling after UNKNOWN runs can be generated: OC-12 needs OC-06/OC-10.

- Integration last: ORCH-IT-01..12 require a complete, certified production server.

# 2.  Sprint Overview

| # | Sprint | Goal | Stories | Pts | Length |
| --- | --- | --- | --- | --- | --- |
| S1 | Persistent Foundation | A versioned .NET Linux container image starts successfully in both Connected and Isolated modes, binds its API endpoints at the correct network scope, and persi… | OC-16, OC-15 | 21 | 2 weeks |
| S2 | Identity | Runtime workers can register their capabilities and receive a stable identity; the Designer can publish immutable signed automation artifacts. Both registries s… | OC-01, OC-11 | 21 | 2 weeks |
| S3 | Job Intake and Queue Dispatch | An operator can submit a job via API or cron schedule; the Orchestrator validates the script reference, creates a QUEUED run, and offers it exclusively to the f… | OC-02, OC-03 | 21 | 2 weeks |
| S4 | Lease Lifecycle | A worker holds an exclusively AttemptId-fenced execution slot, keeps it alive with heartbeats, and can receive a cancellation signal. A Desktop screen-lock wait… | OC-04, OC-05, OC-09 | 26 | 2 weeks |
| S5 | Run Completion | Every run produces a definitively immutable terminal outcome. Orchestrator restarts and worker disconnects cannot corrupt committed state or silently re-execute… | OC-06, OC-10 | 21 | 2 weeks |
| S6 | Async Handoff | An authenticated, HMAC-signed business-service callback is deduplicated, correlated to a confirmed HANDED_OFF run, and triggers exactly one preconfigured contin… | OC-07, OC-08, OC-17 | 29 | 2 weeks |
| S7 | Operator Tooling | Operators can investigate and resolve every UNKNOWN run with a full audit trail; an admin API gives complete operational visibility and control; structured tele… | OC-12, OC-13, OC-14 | 24 | 2 weeks |
| S8 | Integration Validation and Release Certification | The production Orchestrator passes the Stage 1 CEC conformance suite with a genuine Desktop Runtime client. All 12 cross-component integration scenarios are evi… | ORCH-IT-01, ORCH-IT-02, ORCH-IT-03, ORCH-IT-04, ORCH-IT-05, ORCH-IT-06, ORCH-IT-07, ORCH-IT-08, ORCH-IT-09, ORCH-IT-10, ORCH-IT-11, ORCH-IT-12 | 36 | 2 weeks |

# 3.  Story Point Burndown

| Sprint | Theme | Points | Running | Sprint Goal (summary) |
| --- | --- | --- | --- | --- |
| S1 | Container, Database and Deployment | 21 | 21 | A blank Orchestrator container starts in either mode, passes the health check, and survives a forced restart without state loss. |
| S2 | Worker Registration and Artifact Registry | 21 | 42 | A Desktop worker registers and is visible in the registry. A Designer publishes a v1 signed artifact. Both survive container restart. |
| S3 | Job Intake and Queue Dispatch | 21 | 63 | End-to-end: operator POSTs a job → it queues → Desktop worker PullJob call receives JobOffered. No double-offer under concurrent load. |
| S4 | Hold, Heartbeat, Cancel | 26 | 89 | Full lease lifecycle demonstrated: PullJob → AcceptLease → heartbeat loop → cancellation → CANCELLED result. AttemptId fencing verified under concurrent attempts. |
| S5 | Terminal Outcomes and Reconciliation | 21 | 110 | Every run reaches a terminal state and stays there. A simulated crash during execution reconciles to UNKNOWN + NEEDS_ATTENTION, never silently to SUCCEEDED. |
| S6 | Callbacks, Continuation and Security Hardening | 29 | 139 | Full multi-run chain demonstrated: Run A → HANDED_OFF → authenticated callback → Run B QUEUED. Static SUCCEEDED→Run B also verified. All API boundaries reject unauthenticated requests. |
| S7 | Admin, UNKNOWN Resolution and Observability | 24 | 163 | An operator can list UNKNOWN runs, drill into a run's journal, resolve it with audit trail, export a diagnostic bundle, and see correlated Orchestrator + Desktop Runtime traces for the same run. |
| S8 | Integration Validation and Release Certification | 36 | 199 | All 12 ORCH-IT scenarios have passing integration evidence. Stage 1 conformance suite passes. POC-01..09 evaluated for isolated mode (POC-10 separate gate for connected unattended session). Release notes and certification document updated. |

# 4.  Dependency Map

| Sprint | Story | Title | Depends on | Blocks |
| --- | --- | --- | --- | --- |
| S1 | OC-16 | Deployment: Connected and Isol… | — | OC-15 and all subsequent stories |
| S1 | OC-15 | Persistence, Durability and Re… | OC-16 | OC-01, OC-11, OC-02, OC-03, OC-04, OC-05, OC-06, OC-10, OC-07, OC-08 |
| S2 | OC-01 | Worker Registration and Capabi… | OC-15 | OC-03, OC-04, OC-09 |
| S2 | OC-11 | Script and Artifact Registry | OC-15 | OC-02, OC-04, OC-08 |
| S3 | OC-02 | Job Intake: Manual, Scheduled … | OC-11, OC-15 | OC-03 |
| S3 | OC-03 | Queue Management and Worker Ca… | OC-01, OC-02, OC-15 | OC-04, OC-09 |
| S4 | OC-04 | Lease Offer, Acceptance and At… | OC-03, OC-11, OC-15 | OC-05, OC-09, OC-06 |
| S4 | OC-05 | Heartbeat Processing and Lease… | OC-04 | OC-09, OC-06, OC-10 |
| S4 | OC-09 | Cancellation | OC-04, OC-05 | ORCH-IT-06 |
| S5 | OC-06 | Final Result Processing and At… | OC-04, OC-05, OC-01 | OC-10, OC-07, OC-08, OC-12 |
| S5 | OC-10 | Reconciliation After Disconnec… | OC-05, OC-06 | OC-12, ORCH-IT-03, ORCH-IT-09 |
| S6 | OC-07 | Asynchronous Callback Intake a… | OC-06, OC-15 | OC-08 |
| S6 | OC-08 | Continuation Mapping and Run B… | OC-07, OC-02, OC-11 | ORCH-IT-07, ORCH-IT-08 |
| S6 | OC-17 | Security Controls | OC-01..OC-10 | ORCH-IT-12 |
| S7 | OC-12 | UNKNOWN Runs and Operator Reso… | OC-06, OC-10, OC-13 | ORCH-IT-09 |
| S7 | OC-13 | Admin and Operator API | OC-02, OC-06, OC-10, OC-14 | OC-12 |
| S7 | OC-14 | Telemetry and Observability | All OC-01..OC-10 transitions | ORCH-IT-10 |
| S8 | ORCH-IT-01 | interactiveSessionId exclusive… | All OC stories | Release gate |
| S8 | ORCH-IT-02 | leaseGranted content integrity | All OC stories | Release gate |
| S8 | ORCH-IT-03 | Power-loss / restart during ir… | All OC stories | Release gate |
| S8 | ORCH-IT-04 | Idempotency under duplication | All OC stories | Release gate |
| S8 | ORCH-IT-05 | Heartbeat during Desktop scree… | All OC stories | Release gate |
| S8 | ORCH-IT-06 | Cancellation during held mouse… | All OC stories | Release gate |
| S8 | ORCH-IT-07 | serviceOutcome routing and sin… | All OC stories | Release gate |
| S8 | ORCH-IT-08 | Static SUCCEEDED continuation … | All OC stories | Release gate |
| S8 | ORCH-IT-09 | Operator UNKNOWN investigation… | All OC stories | Release gate |
| S8 | ORCH-IT-10 | Mock and production semantic c… | All OC stories | Release gate |
| S8 | ORCH-IT-11 | Isolated host loopback isolati… | All OC stories | Release gate |
| S8 | ORCH-IT-12 | Offline signed artifact import | All OC stories | Release gate |

# 5.  Sprint Details

Sprint 1  Persistent Foundation — Container, Database and Deployment

| Sprint Goal | A versioned .NET Linux container image starts successfully in both Connected and Isolated modes, binds its API endpoints at the correct network scope, and persists all state changes durably across container restarts — forming the stable foundation every later sprint depends on. |
| --- | --- |
| Duration | 2 weeks ¦ Story Points: 21 |
| Sprint DoD | A blank Orchestrator container starts in either mode, passes the health check, and survives a forced restart without state loss. |
| Key Risk / Pre-condition | WSL2 volume persistence may require platform-team coordination for isolated-mode DB path. |

### OC-16  —  Deployment: Connected and Isolated Modes  (8 pts)

Why in this sprint: Must be first — every other story needs a running, correctly bound container before it can be tested or delivered.

Acceptance Criteria

- Container starts in Connected mode: approved network ingress, authenticated TLS endpoint, role-specific controls.

- Container starts in Isolated mode: Windows host publication/firewall restricts access to loopback; authorized Executor can reach it; remote hosts rejected.

- Health endpoint GET /health → 200 OK with status=healthy, dbConnected=true, queueDepth=N.

- CI: docker run confirms no Windows-only DLLs (P/Invoke, WPF, Registry) in image.

- TRACTO_MODE env var switches mode; invalid value fails startup with clear error.

Dependencies

None — this is the base story.

Tests

Unit: mode-switching; Integration (POC-01, POC-03): Supervisor starts container, Executor connects.

### OC-15  —  Persistence, Durability and Restart Recovery  (13 pts)

Why in this sprint: Durability guarantees underpin every state machine transition in sprints 2–8. Without atomic commits the whole run lifecycle is unsafe.

Acceptance Criteria

- State committed then container crashes → persisted state survives restart.

- In-flight RUNNING job on restart → state=RUNNING preserved; worker resumes heartbeat.

- Worker crashed too → absence threshold triggers reconciliation; UNKNOWN if no journal.

- DB migration runs atomically at container start; rollback on failure; older records readable.

- Isolated mode: SQLite DB file in WSL volume survives Docker Engine restart.

Dependencies

OC-16 (container must exist and bind before persistence layer can be tested).

Tests

Unit: commit-then-crash with in-memory SQLite; Integration (POC-06): WSL crash recovery.

Sprint 2  Identity — Worker Registration and Artifact Registry

| Sprint Goal | Runtime workers can register their capabilities and receive a stable identity; the Designer can publish immutable signed automation artifacts. Both registries survive restart and guard against tampering. |
| --- | --- |
| Duration | 2 weeks ¦ Story Points: 21 |
| Sprint DoD | A Desktop worker registers and is visible in the registry. A Designer publishes a v1 signed artifact. Both survive container restart. |
| Key Risk / Pre-condition | Artifact signing toolchain (trusted publisher key) must be confirmed with the security team before this sprint. |

### OC-01  —  Worker Registration and Capability Advertisement  (8 pts)

Why in this sprint: Workers must exist in the registry before jobs can be dispatched. Capability indexing built here drives the matching in OC-03.

Acceptance Criteria

- Authenticated Desktop worker registers with all required fields → workerId returned; state=AVAILABLE.

- Re-registration by same authenticated worker is idempotent; surviving LEASED/RUNNING attempts are not released.

- Missing runtimeType → 400; nothing persisted.

- capabilityDigest mismatch → rejected/flagged; digest is integrity hint only, not auth.

- No-heartbeat for > absenceThreshold → worker OFFLINE; RUNNING jobs enter reconciliation.

Dependencies

OC-15 (worker records must be durably persisted).

Tests

Unit: registration, re-registration fencing, missing-field rejection; Integration: Mock.Orchestrator client registration.

### OC-11  —  Script and Artifact Registry  (13 pts)

Why in this sprint: Job intake (OC-02) validates scriptVersionRef against the registry. Without OC-11 no job can be admitted.

Acceptance Criteria

- Valid signed artifact → stored immutably; version record written.

- Overwrite attempt on existing version → 409.

- Unsupported schemaVersion → 422 with diagnostic; initial launch validates v1 and unsupported versions.

- Prohibited business-logic expression → 422 with violation location.

- Worker fetches artifact at lease time → immutable content; ETag/hash cacheable.

- Delete with active LEASED/RUNNING lease → 409.

- Desktop-specific selector content preserved opaque; Desktop worker validates its own selectors.

Dependencies

OC-15 (artifact bytes and metadata must be durably stored).

Tests

Unit: valid/invalid artifacts, overwrite, delete-with-lease; Integration: Designer publish → worker fetch.

Sprint 3  Job Intake and Queue Dispatch

| Sprint Goal | An operator can submit a job via API or cron schedule; the Orchestrator validates the script reference, creates a QUEUED run, and offers it exclusively to the first capable, available, eligible worker. |
| --- | --- |
| Duration | 2 weeks ¦ Story Points: 21 |
| Sprint DoD | End-to-end: operator POSTs a job → it queues → Desktop worker PullJob call receives JobOffered. No double-offer under concurrent load. |
| Key Risk / Pre-condition | interactiveSessionId exclusivity requires DB-level locking strategy confirmed before sprint starts. |

### OC-02  —  Job Intake: Manual, Scheduled and Event Triggers  (8 pts)

Why in this sprint: Core entry point for all automation. Without intake there is nothing to dispatch.

Acceptance Criteria

- Manual POST /jobs → runId returned; state=CREATED→QUEUED.

- Cron trigger → job created with same validation; correlationId generated.

- Callback with continuationScriptRef → 400; no job created.

- scriptVersionRef not in registry → 422.

- Unsupported schemaVersion → 422 (v1 only at initial release).

- Duplicate eventId within window → 200 DUPLICATE; job count = 1.

- Deadline in the past → 422.

Dependencies

OC-11 (artifact validation at intake), OC-15 (run record persisted).

Tests

Unit: all intake paths; cron trigger; duplicate eventId; Integration: scheduled job at correct time.

### OC-03  —  Queue Management and Worker Capability Matching  (13 pts)

Why in this sprint: The exclusive offer mechanism is the heart of dispatch. Concurrency safety (no double-offer) and interactiveSessionId exclusivity must be correct before lease work begins.

Acceptance Criteria

- Capable worker → JobOffered exclusively; no concurrent double-offer.

- Wrong runtimeType → NoPendingJob; job stays QUEUED.

- Worker already active → NoPendingJob (one-job-per-worker).

- Concurrent PullJob race → exactly one JobOffered; other NoPendingJob.

- Queue depth at max → 503 with Retry-After on new intake.

- Mixed-engine script → 422 at intake.

- Two headed workers share interactiveSessionId; one holds input lease → no second input-owning offer.

- Worker missing required action capability or unsupported protocol major → no incompatible job offered.

Dependencies

OC-01 (worker records), OC-02 (job records), OC-15 (queue persisted).

Tests

Unit: matching, no-match, one-per-worker; Concurrency: race on PullJob; Unit: session exclusivity.

Sprint 4  Lease Lifecycle — Hold, Heartbeat, Cancel

| Sprint Goal | A worker holds an exclusively AttemptId-fenced execution slot, keeps it alive with heartbeats, and can receive a cancellation signal. A Desktop screen-lock wait stays RUNNING throughout. |
| --- | --- |
| Duration | 2 weeks ¦ Story Points: 26 |
| Sprint DoD | Full lease lifecycle demonstrated: PullJob → AcceptLease → heartbeat loop → cancellation → CANCELLED result. AttemptId fencing verified under concurrent attempts. |
| Key Risk / Pre-condition | Late-AcceptLease requeue decision (non-start must be affirmatively established) requires explicit policy from architecture owner before coding. |

### OC-04  —  Lease Offer, Acceptance and AttemptId Fencing  (13 pts)

Why in this sprint: Lease acceptance transitions LEASED→RUNNING and arms the heartbeat. AttemptId fencing is the primary correctness invariant for the entire run lifecycle.

Acceptance Criteria

- AcceptLease within window → RUNNING; timestamp recorded; attemptId confirmed.

- Late AcceptLease → 409; requeue only if non-start definitively established; otherwise UNKNOWN/reconciliation.

- Different-worker AcceptLease → 409 fenced.

- Wrong attemptId → 409.

- Lease payload contains no resolved secrets.

- Pinned artifact immutable; deletion of referenced artifact prohibited while leased.

- Same authenticated worker repeats identical leaseAccepted → idempotent; no second attempt.

Dependencies

OC-03 (lease offered), OC-11 (artifact pinned), OC-15 (lease state persisted).

Tests

Unit: valid/late/duplicate/wrong accept; same-worker idempotency; lease payload secret assertion.

### OC-05  —  Heartbeat Processing and Lease Expiry  (8 pts)

Why in this sprint: Heartbeat is the liveness signal for every RUNNING job. Lease expiry feeds OC-10 reconciliation.

Acceptance Criteria

- Valid heartbeat → lastHeartbeatAt updated; 200 returned.

- Stale seqNo → not accepted; expiry timer not reset.

- Missed heartbeat → lease flagged suspect/expired internally (no new run state); reconciliation required before any disposition.

- Heartbeat response carries cancellationRequested=true when cancel pending.

- Post-restart: heartbeat accepted for valid unfenced attempt; otherwise worker directed to reconcile.

- Worker shorter interval → Orchestrator enforces its own expiry window.

Dependencies

OC-04 (RUNNING lease must exist).

Tests

Unit: valid, stale-seq, missed; cancel-signal delivery; restart recovery.

### OC-09  —  Cancellation  (5 pts)

Why in this sprint: Cancellation is delivered via the heartbeat response path (just built in OC-05) and completes the run control surface.

Acceptance Criteria

- Cancel QUEUED → CANCELLED immediately; no worker interaction.

- Cancel RUNNING → cancellationRequested stored; delivered on next heartbeat response.

- Worker receives flag → releases resources; submits CANCELLED or UNKNOWN.

- Cancel LEASED (before AcceptLease) → CANCELLED; subsequent AcceptLease rejected.

- Cancel HANDED_OFF → rejected; terminal state immutable; Run B unaffected.

- Double-cancel → 200 ALREADY_CANCELLED; idempotent.

Dependencies

OC-04 (LEASED state), OC-05 (heartbeat delivery path).

Tests

Unit: cancel at each pre-terminal state; Integration: Desktop worker receives cancel, submits CANCELLED.

Sprint 5  Run Completion — Terminal Outcomes and Reconciliation

| Sprint Goal | Every run produces a definitively immutable terminal outcome. Orchestrator restarts and worker disconnects cannot corrupt committed state or silently re-execute irreversible actions. |
| --- | --- |
| Duration | 2 weeks ¦ Story Points: 21 |
| Sprint DoD | Every run reaches a terminal state and stays there. A simulated crash during execution reconciles to UNKNOWN + NEEDS_ATTENTION, never silently to SUCCEEDED. |
| Key Risk / Pre-condition | UNKNOWN terminal requires a reliable "no-postcondition-proof" detection strategy that must be agreed with the Desktop Runtime team. |

### OC-06  —  Final Result Processing and AttemptId Commit  (8 pts)

Why in this sprint: Completes the run state machine. Without terminal result handling there are no SUCCEEDED/FAILED/HANDED_OFF runs to reason about in later sprints.

Acceptance Criteria

- SUCCEEDED with matching attemptId → persisted; worker slot released; evidence refs stored.

- UNKNOWN → needsAttention=true; unknownReason stored; no auto-replay.

- Stale/different attemptId → 409 fenced.

- HANDED_OFF with businessJobId → persisted; businessJobId stored for OC-07 correlation.

- SUCCEEDED + businessOutcome=REJECTED → SUCCEEDED persisted; businessOutcome stored as-is.

- Sensitive plaintext in payload → rejected/quarantined; security event emitted.

- Worker slot released exactly once after terminal commit.

- Identical finalResult retry → idempotent; no duplicate history or slot release.

Dependencies

OC-04/05 (RUNNING lease), OC-01 (worker slot management).

Tests

Unit: all terminal states, idempotent retry, stale-attemptId, slot release.

### OC-10  —  Reconciliation After Disconnect or Restart  (13 pts)

Why in this sprint: Reconciliation is the safety net that prevents silent re-execution when connectivity is lost. Must be built in the same sprint as OC-06 so the full terminal path (including UNKNOWN) is end-to-end consistent.

Acceptance Criteria

- Journal shows SUCCEEDED + correct attemptId → state=SUCCEEDED.

- Uncertain journal → UNKNOWN + NEEDS_ATTENTION; no replay.

- Stale attemptId → 409.

- Post-restart heartbeat: accepted for valid unfenced attempt; run stays RUNNING.

- Empty journal → UNKNOWN + NEEDS_ATTENTION.

- Reconcile does not increment attempt count; original attemptId retained.

Dependencies

OC-05 (lease expiry marks lease suspect), OC-06 (terminal state commitment).

Tests

Unit: all journal scenarios; Integration: Orchestrator restart mid-job; worker reconciles → correct terminal state.

Sprint 6  Async Handoff — Callbacks, Continuation and Security Hardening

| Sprint Goal | An authenticated, HMAC-signed business-service callback is deduplicated, correlated to a confirmed HANDED_OFF run, and triggers exactly one preconfigured continuation run. All API boundaries enforce authentication and signed-artifact validation. |
| --- | --- |
| Duration | 2 weeks ¦ Story Points: 29 |
| Sprint DoD | Full multi-run chain demonstrated: Run A → HANDED_OFF → authenticated callback → Run B QUEUED. Static SUCCEEDED→Run B also verified. All API boundaries reject unauthenticated requests. |
| Key Risk / Pre-condition | HMAC key management and key-rotation policy must be confirmed with the security team before sprint starts. |

### OC-07  —  Asynchronous Callback Intake and Replay Protection  (8 pts)

Why in this sprint: Required before OC-08 — the callback is the trigger for continuation.

Acceptance Criteria

- Valid HMAC-signed callback → eventId durably stored; exactly one OC-08 continuation queued after HANDED_OFF confirmed.

- Invalid HMAC → 401; security event emitted.

- Stale timestamp → 401; replay rejected; security event.

- Duplicate eventId → 200 DUPLICATE; continuation count = 1.

- Callback with continuationScriptRef → 400.

- Unknown correlationId → sanitized audit event; no continuation.

- Completed continuation businessJobId → 200 DUPLICATE; no third run.

- Service-supplied automationId/scriptVersionRef → rejected; no dynamic routing.

Dependencies

OC-06 (HANDED_OFF state), OC-15 (durable eventId storage).

Tests

Unit: all 8 ACs; HMAC signing test harness.

### OC-08  —  Continuation Mapping and Run B Creation  (13 pts)

Why in this sprint: Completes the HANDED_OFF flow and adds the static SUCCEEDED continuation path.

Acceptance Criteria

- Valid callback + configured mapping → Run B QUEUED; parent runId linked; businessJobId in inputs.

- Missing target artifact → operator attention record; source terminal state unchanged.

- Callback for non-HANDED_OFF run → 422.

- Run B result does not change Run A state.

- Mapping updated while Run B RUNNING → Run B uses original mapping.

- SUCCEEDED + static preapproved rule → exactly one new Run B; source stays SUCCEEDED.

- FAILED/CANCELLED/TIMED_OUT/UNKNOWN/unmapped HANDED_OFF → no success continuation.

- Duplicate SUCCEEDED notification or callback → no second Run B (durable uniqueness).

Dependencies

OC-07 (callback intake), OC-02 (job creation), OC-11 (artifact validation).

Tests

Unit: callback-driven and static continuations; deduplication; source-state invariance.

### OC-17  —  Security Controls  (8 pts)

Why in this sprint: Sprint 6 is the last feature-rich sprint before operator tooling and observability. Placing security hardening here allows the team to lock down all API surfaces that now exist before the release sprint.

Acceptance Criteria

- Unauthenticated PullJob/heartbeat → 401; security event.

- Valid HMAC callback → accepted; eventId deduplicated.

- Resolved secret in any inbound payload → rejected/redacted; security event; no plaintext stored.

- Bad artifact signature → 422.

- Admin API from IP outside allowlist (Connected mode) → 403.

- No Orchestrator code path calls DPAPI/ProtectedData — confirmed by static analysis.

Dependencies

All prior API endpoints (OC-01..OC-10) must exist before security controls can be systematically verified.

Tests

Unit: auth failures; CI static analysis for DPAPI references; secret scan on event payloads.

Sprint 7  Operator Tooling — Admin, UNKNOWN Resolution and Observability

| Sprint Goal | Operators can investigate and resolve every UNKNOWN run with a full audit trail; an admin API gives complete operational visibility and control; structured telemetry events enable end-to-end trace correlation between Orchestrator and Desktop Runtime. |
| --- | --- |
| Duration | 2 weeks ¦ Story Points: 24 |
| Sprint DoD | An operator can list UNKNOWN runs, drill into a run's journal, resolve it with audit trail, export a diagnostic bundle, and see correlated Orchestrator + Desktop Runtime traces for the same run. |
| Key Risk / Pre-condition | OpenTelemetry OTLP collector configuration for Connected mode requires customer environment setup. |

### OC-12  —  UNKNOWN Runs and Operator Resolution  (8 pts)

Why in this sprint: UNKNOWN runs accumulate from OC-06/OC-10. Operators need resolution tooling before the system is production-safe.

Acceptance Criteria

- UNKNOWN run GET → details include lastJournalEntry, unknownReason, evidenceRefs, NEEDS_ATTENTION.

- INVESTIGATED_NO_RERUN → original UNKNOWN state/history preserved; audited resolution record appended; no replay.

- APPROVED_NEW_RUN → new runId/attemptId; correlation to original; original UNKNOWN immutable.

- Auto-replay without operator approval → must never occur (invariant test).

- Empty justification → 400.

Dependencies

OC-06/OC-10 (UNKNOWN runs must exist), OC-13 (admin API endpoint shared).

Tests

Unit: both resolution paths; empty-justification; invariant: no auto-replay code path.

### OC-13  —  Admin and Operator API  (8 pts)

Why in this sprint: Admin API is the operator's window into the system. The UNKNOWN resolution endpoint (OC-12) and cancellation (OC-09) use it.

Acceptance Criteria

- Filter runs by status=UNKNOWN and date → paginated list.

- View full run detail → evidenceRef URIs; no secret values.

- Create continuation mapping → stored; version-pinned; audit record.

- Trigger manual job → equivalent to OC-02-AC01.

- Unauthenticated request → 401.

- Export telemetry bundle → signed; run log, step events, evidenceRefs; no secrets or domain data.

Dependencies

OC-02 (jobs), OC-06 (runs), OC-10 (reconciliation data), OC-14 (telemetry for export).

Tests

Unit: all 6 ACs; unauthenticated-request rejection; bundle export content scan.

### OC-14  —  Telemetry and Observability  (8 pts)

Why in this sprint: Telemetry must be in place before the integration sprint so ORCH-IT scenarios can be verified by evidence.

Acceptance Criteria

- Every state transition → structured event with runId, workerId, leaseId, attemptId, timestamp, eventType.

- SUCCEEDED finalResult → event includes stepCount, durationMs, businessOutcome if present.

- Bad-HMAC callback → CALLBACK_AUTH_FAILED security event; source IP; no callback content.

- No plaintext secret or domain payload in any event; opaque refs omitted/redacted.

- Isolated mode export → signed bundle; events within retention; size-bounded.

- runId + attemptId in both Orchestrator and Runtime telemetry for same run (OTLP correlation).

Dependencies

All prior stories (events fire from every state transition).

Tests

Unit: events for all transitions; resolved-secret scan; correlated runId in mock Runtime event.

Sprint 8  Integration Validation and Release Certification

| Sprint Goal | The production Orchestrator passes the Stage 1 CEC conformance suite with a genuine Desktop Runtime client. All 12 cross-component integration scenarios are evidenced. POC-01..09 are evaluated. The system is release-certified. |
| --- | --- |
| Duration | 2 weeks ¦ Story Points: 36 |
| Sprint DoD | All 12 ORCH-IT scenarios have passing integration evidence. Stage 1 conformance suite passes. POC-01..09 evaluated for isolated mode (POC-10 separate gate for connected unattended session). Release notes and certification document updated. |
| Key Risk / Pre-condition | Requires real Desktop Runtime client, WSL2 environment, Docker Engine and (for Connected mode) a network-accessible deployment. |

### ORCH-IT-01  —  interactiveSessionId exclusive input lease across workers  (3 pts)

Acceptance Criteria

- Register Desktop and headed Browser with same interactiveSessionId; verify only one foreground-input lease active at a time.

Dependencies

OC-01, OC-03, OC-04.

Tests

Integration: two-worker session contention; verified under concurrent PullJob.

### ORCH-IT-02  —  leaseGranted content integrity  (3 pts)

Acceptance Criteria

- leaseGranted carries pinned hash/version, attempt identity and input references received by Desktop; no resolved secret in any field.

Dependencies

OC-04.

Tests

Integration: Desktop worker reads lease; asserts hash and no plaintext secret.

### ORCH-IT-03  —  Power-loss / restart during irreversible click  (3 pts)

Acceptance Criteria

- Simulate power-loss during Desktop click; after recovery reconcile same attempt without double-click; UNKNOWN if commit unprovable.

Dependencies

OC-05, OC-10.

Tests

Integration: staged crash during execute; reconciliation journal inspection.

### ORCH-IT-04  —  Idempotency under duplication  (3 pts)

Acceptance Criteria

- Duplicate leaseAccepted, heartbeat, finalResult and callback are all idempotent; stale competing attempt cannot change terminal state.

Dependencies

OC-04, OC-05, OC-06, OC-07.

Tests

Integration: replay each message type; assert state count = 1.

### ORCH-IT-05  —  Heartbeat during Desktop screen-lock wait  (3 pts)

Acceptance Criteria

- Desktop heartbeats continue during bounded locked-session wait; no PAUSED state; no new job dispatched to that session.

Dependencies

OC-03, OC-05.

Tests

Integration: lock Windows session; Desktop continues heartbeat; no new dispatch.

### ORCH-IT-06  —  Cancellation during held mouse button  (3 pts)

Acceptance Criteria

- Cancel during Desktop held mouse delivered on next poll/heartbeat; Desktop cleanup determines CANCELLED vs UNKNOWN; Orchestrator does not force false success.

Dependencies

OC-05, OC-09.

Tests

Integration: cancel mid-hold; Desktop reports CANCELLED; Orchestrator records correctly.

### ORCH-IT-07  —  serviceOutcome routing and single Run B  (3 pts)

Acceptance Criteria

- Runtime accepts sync serviceOutcome without Orchestrator routing business logic; callback after HANDED_OFF creates exactly one mapped Run B.

Dependencies

OC-06, OC-07, OC-08.

Tests

Integration: HANDED_OFF → callback → single Run B; duplicate callback → idempotent.

### ORCH-IT-08  —  Static SUCCEEDED continuation fires exactly once  (3 pts)

Acceptance Criteria

- SUCCEEDED triggers configured static next run once; FAILED/CANCELLED/TIMED_OUT/UNKNOWN/unmapped HANDED_OFF do not trigger success rule.

Dependencies

OC-06, OC-08.

Tests

Integration: SUCCEEDED → one Run B; FAILED → no Run B; duplicate SUCCEEDED → still one Run B.

### ORCH-IT-09  —  Operator UNKNOWN investigation and new-run authorization  (3 pts)

Acceptance Criteria

- Operator appends audited resolution to UNKNOWN; can authorize distinct new run; original terminal status and journal stay immutable.

Dependencies

OC-10, OC-12, OC-13.

Tests

Integration: UNKNOWN run → resolve → assert original unchanged; new run has new runId.

### ORCH-IT-10  —  Mock and production semantic conformance  (3 pts)

Acceptance Criteria

- Stage 1 Mock and production Orchestrator share logical message semantics; Connected and Isolated deployments preserve published messages and security guarantees.

Dependencies

All OC stories.

Tests

Integration: Stage 1 conformance suite run against production server with Desktop Runtime client.

### ORCH-IT-11  —  Isolated host loopback isolation  (3 pts)

Acceptance Criteria

- Isolated host-side access is loopback-limited; Windows Executor can reach Orchestrator; remote client attempts fail.

Dependencies

OC-16.

Tests

Integration: POC-01; remote connection attempt rejected; Executor localhost connection succeeds.

### ORCH-IT-12  —  Offline signed artifact import  (3 pts)

Acceptance Criteria

- Designer artifact imported offline with valid signature is retrievable identically by worker; tampered or unsupported package rejected before execution.

Dependencies

OC-11, OC-17.

Tests

Integration: signed offline bundle import; tampered bundle rejected; valid bundle fetched by worker.

# 6.  Release Definition of Done

The Orchestrator is release-ready when all of the following are met:

- All OC-01–OC-17 acceptance criteria pass with actual unit/integration/security evidence.

- All ORCH-IT-01–12 integration scenarios pass with real Desktop Runtime client.

- Stage 1 CEC conformance suite passes against the production server.

- No code path in the Orchestrator binary resolves secrets (DPAPI/ProtectedData → zero grep matches in CI).

- Isolated deployment passes POC-01..09; Connected deployment passes authenticated central ingress and persistence tests.

- POC-10 (connected unattended session) requires separate evidence — do not record as passed without it.

- All transport/endpoint names verified against actual Stage 1 release artifacts; unresolved choices recorded.

- CERTIFICATION.md updated with sprint evidence and release signoff.